## TEST CASES(FUNCTIONAL)
Kedebah Payroll — QA Master Summary | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS |  | EXECUTIVE SUMMARY |  |  |  |  | COUNTS | PERCENTAGE (%)
|  | 2026-07-01 | Deffect count: Recommendations count: |  | Black | Pass/Fixed | Total executed | 441 | Open Defects | 12 |  | N# of Test Objectives | % of Fail
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed | PASS | 260 | Catalogue cases | 417 |  | Pending Count | % of Pass
[5 empty] | Blue | Recommendations | FAIL | 3 | Pass rate (of exec) | 99% |  | Pass Count | % of Pending
[7 empty] | BLOCKED | 178 |  |  |  | Fail Count | % of Recommendation
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com | [6 empty] | NOT APPLICABLE | 0 |  |  |  | Recommendation Count | No Status
WORKBOOK | TOTAL | PASS | FAIL | BLOCKED | N/A | DEFECTS | PASS RATE | FILE | TEST STATUS | COMMENTS/NOTES | ATTACHMENTS | Total | Total
01-Dashboard | 5 | 1 | 1 | 3 | 0 | 0 | 50% | 01-Dashboard.xlsx
02-Authentication | 19 | 9 | 1 | 9 | 0 | 0 | 90% | 02-Authentication.xlsx
03-Employees | 34 | 21 | 0 | 13 | 0 | 1 | 100% | 03-Employees.xlsx
04-Bank Setup | 16 | 12 | 0 | 4 | 0 | 1 | 100% | 04-Bank Setup.xlsx
05-Pay Groups | 12 | 3 | 0 | 9 | 0 | 1 | 100% | 05-Pay Groups.xlsx
06-PAYE | 17 | 16 | 0 | 1 | 0 | 0 | 100% | 06-PAYE.xlsx
07-Tax | 31 | 17 | 0 | 14 | 0 | 4 | 100% | 07-Tax.xlsx
08-Reliefs | 8 | 1 | 0 | 7 | 0 | 1 | 100% | 08-Reliefs.xlsx
09-Special Tax | 23 | 10 | 0 | 13 | 0 | 0 | 100% | 09-Special Tax.xlsx
10-Calculation Engine | 24 | 15 | 0 | 9 | 0 | 0 | 100% | 10-Calculation Engine.xlsx
11-Pay Schedule | 20 | 12 | 1 | 7 | 0 | 0 | 92% | 11-Pay Schedule.xlsx
12-Pay Runs | 22 | 20 | 0 | 2 | 0 | 0 | 100% | 12-Pay Runs.xlsx
13-Payroll Lifecycle | 20 | 12 | 0 | 8 | 0 | 1 | 100% | 13-Payroll Lifecycle.xlsx
14-Benefits | 16 | 10 | 0 | 6 | 0 | 0 | 100% | 14-Benefits.xlsx
15-Benefits In Kind | 16 | 12 | 0 | 4 | 0 | 0 | 100% | 15-Benefits In Kind.xlsx
16-Deductions | 25 | 10 | 0 | 15 | 0 | 0 | 100% | 16-Deductions.xlsx
17-Loans | 16 | 12 | 0 | 4 | 0 | 0 | 100% | 17-Loans.xlsx
18-Alerts | 16 | 12 | 0 | 4 | 0 | 0 | 100% | 18-Alerts.xlsx
19-Payments | 18 | 12 | 0 | 6 | 0 | 0 | 100% | 19-Payments.xlsx
20-Payslips | 16 | 7 | 0 | 9 | 0 | 0 | 100% | 20-Payslips.xlsx
21-Reports | 15 | 10 | 0 | 5 | 0 | 0 | 100% | 21-Reports.xlsx
22-Compliance | 10 | 7 | 0 | 3 | 0 | 0 | 100% | 22-Compliance.xlsx
23-Security | 18 | 8 | 0 | 10 | 0 | 1 | 100% | 23-Security.xlsx
24-Settings | 1 | 1 | 0 | 0 | 0 | 0 | 100% | 24-Settings.xlsx
25-Enterprise Onboarding | 23 | 10 | 0 | 13 | 0 | 2 | 100% | 25-Enterprise Onboarding.xlsx
GRAND TOTAL | 441 | 260 | 3 | 178 | 0 | 12 | 99%
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## DEFECTS TRACKING
TEST TITLE | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: Functional/Non Functional
DEFECT ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | ASSIGNED TO | STATUS | RESOLUTION DATE/TIME | LINKED TEST CASE ID
DF01 | System crashes when creating job position roles | 1. Navigate to Recruitment module 2. Select 'Create Job Position' 3. Save | [Developer Name] | Open | [Insert Date] | TC01
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## NON-FUNCTIONAL TESTING
TEST TITLE | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: PERFORMANCE TESTING
TEST CASE ID | PERFORMANCE CRITERIA | TEST SCENARIO | EXPECTED PERFORMANCE | ACTUAL PERFORMANCE | DEVIATION | COMMENTS
PT01 | Response time < 2 sec | Load Testing | Creating job roles should take < 2 sec | [Insert Observed Time] | [Insert Deviation] | [Insert Comments]
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: SECURITY TESTING
TEST CASE ID | SECURITY ASPECT TESTED | VULNERABILITY FOUND | RISK LEVEL
ST01 | Data Integrity | No issues | Low
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: USABILITY TESTING
TEST CASE ID | USERABILITY CRITERIA | USER TEST FEEDBACK
UT01 | Ease of use | Positive feedback from HR team
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: COMPATIBILITY TESTING
TEST CASE ID | PLATFORM TESTED | COMPATIBILITY ISSUES
CT01 | Windows, macOS | None
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )