## TEST CASES(FUNCTIONAL)
Dashboard | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS |  | EXECUTIVE SUMMARY |  |  |  |  | COUNTS | PERCENTAGE (%)
|  | 2026-07-01 | Deffect count: Recommendations count: |  | Black | Pass/Fixed | Total Test Cases | 5 | Pass rate (of exec) | 50% |  | N# of Test Objectives | % of Fail
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed | PASS | 1 | Execution Date | 2026-07-01 |  | Pending Count | % of Pass
[5 empty] | Blue | Recommendations | FAIL | 1 | Environment | SBX |  | Pass Count | % of Pending
[7 empty] | BLOCKED | 3 |  |  |  | Fail Count | % of Recommendation
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com | [6 empty] | NOT APPLICABLE | 0 |  |  |  | Recommendation Count | No Status
TEST CASE ID | TEST CASE DESCRIPTION | PRE-CONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | TEST STATUS | COMMENTS/NOTES | ATTACHMENTS | Total | Total
TC-DASH-001 | Post-login landing renders | Logged in | Land after login |  | Dashboard/landing renders without error | landing data served via /dashboard/summary | Medium | P2 | PASS | ✓ Verified | test-cases/Dashboard
TC-DASH-002 | No console/network errors | Logged in | Load dashboard; capture console + network |  | No JS errors, no failed requests | console=1 jsErr=0 failedReq=2 (0:index.global.min.css,404:index.global.min.css) | Medium | P2 | FAIL | Failed — BR-004 | evidence/browser/settings/hub-desktop.png
TC-DASH-003 | Permission-appropriate widgets | Admin vs Manager vs Staff | Load per role |  | Only permitted widgets/links shown (cross-ref AUTH-009) | BLOCKED — Credentials: permission-appropriate dashboard widgets are role-gated; verifying requires a non-admin (Manager/Staff) session. | Medium | P2 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Dashboard
TC-DASH-004 | Navigation from dashboard | Logged in | Click each nav entry point |  | Routes resolve to correct modules | BLOCKED — Bucket C: dashboard navigation is browser/UI on a Payroll-module page; needs module access (BUG-011). | Low | P3 | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | test-cases/Dashboard
TC-DASH-005 | Responsive rendering | Logged in | View at desktop/tablet/mobile |  | Layout adapts, no broken elements | BLOCKED — UI-only — needs browser-driven (Playwright page) test | Low | P3 | BLOCKED | Blocked – Browser Only | test-cases/Dashboard
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## DEFECTS TRACKING
Dashboard — Defects | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
DEFECT ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | ASSIGNED TO | STATUS | RESOLUTION DATE/TIME | LINKED TEST CASE ID
DF01 | System crashes when creating job position roles | 1. Navigate to Recruitment module 2. Select 'Create Job Position' 3. Save | [Developer Name] | Open | [Insert Date] | TC01
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## NON-FUNCTIONAL TESTING
Dashboard — Non-Functional | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
TEST CASE ID | PERFORMANCE CRITERIA | TEST SCENARIO | EXPECTED PERFORMANCE | ACTUAL PERFORMANCE | DEVIATION | COMMENTS
PT01 | Response time < 2 sec | Load Testing | Creating job roles should take < 2 sec | [Insert Observed Time] | [Insert Deviation] | [Insert Comments]
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: SECURITY TESTING
TEST CASE ID | SECURITY ASPECT TESTED | VULNERABILITY FOUND | RISK LEVEL
ST01 | Data Integrity | No issues | Low
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: USABILITY TESTING
TEST CASE ID | USERABILITY CRITERIA | USER TEST FEEDBACK
UT01 | Ease of use | Positive feedback from HR team
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: COMPATIBILITY TESTING
TEST CASE ID | PLATFORM TESTED | COMPATIBILITY ISSUES
CT01 | Windows, macOS | None
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )