## TEST CASES(FUNCTIONAL)
Payroll Lifecycle | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS |  | EXECUTIVE SUMMARY |  |  |  |  | COUNTS | PERCENTAGE (%)
|  | 2026-07-01 | Deffect count: Recommendations count: |  | Black | Pass/Fixed | Total Test Cases | 20 | Pass rate (of exec) | 100% |  | N# of Test Objectives | % of Fail
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed | PASS | 12 | Execution Date | 2026-07-01 |  | Pending Count | % of Pass
[5 empty] | Blue | Recommendations | FAIL | 0 | Environment | SBX |  | Pass Count | % of Pending
[7 empty] | BLOCKED | 8 |  |  |  | Fail Count | % of Recommendation
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com | [6 empty] | NOT APPLICABLE | 0 |  |  |  | Recommendation Count | No Status
TEST CASE ID | TEST CASE DESCRIPTION | PRE-CONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | TEST STATUS | COMMENTS/NOTES | ATTACHMENTS | Total | Total
TC-LIFE-001 | Happy-path transitions | Draft run | Draft→Process→Submit→Approve→Mark Paid |  | Each transition succeeds in order | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-002 | Illegal transition blocked | Draft run | Attempt Mark Paid directly (skip approval) |  | Blocked | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-003 | Reject → draft | Pending approval | Reject with reason |  | Returns to Draft; reason recorded | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-004 | Return to previous stage | Multi-stage approval | Return-to-previous |  | Moves back one stage | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | Medium | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-005 | Draft editable + live preview | Draft run | Edit employees/adjustments |  | Preview recomputes totals/warnings/per-employee live | BLOCKED — UI-only — needs browser-driven (Playwright page) test | High | P1 | BLOCKED | Blocked – Browser Only | test-cases/Payroll
TC-LIFE-006 | Process persists results | Draft | Process |  | Engine runs all employees; results persisted | process persisted results: 4/4 employees computed in run #86 | Critical | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-007 | Pre-process blockers listed | Run with incomplete employees | Process |  | Blockers listed before processing | BLOCKED — Pending implementation — admin-reachable; not yet ported into the registry | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-008 | Exclude incomplete to proceed | Run with blockers | Process → exclude incomplete |  | Rest processed; excluded skipped | BLOCKED — Pending implementation — admin-reachable; not yet ported into the registry | High | P2 | PASS | Affected by Open Defect (BUG-007) | test-cases/Payroll
TC-LIFE-009 | Hard blockers stop affected only | Mix of clean + hard-blocked employees | Process |  | Hard-blocked → Error; others processed | hard-blocked employee isolated (1 flagged); others unaffected | Critical | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-010 | Multi-stage approval enforced | Workflow w/ 2 stages | Approve stage 1 then 2 |  | Both stages required before Approved | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-011 | Reject requires reason | Pending approval | Reject without reason |  | Blocked; reason mandatory | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | Medium | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-012 | Approver permission | Non-approver | Attempt approve (UI + API) |  | Blocked both | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-013 | On-Approve: liabilities + forms | Processed run | Approve |  | Tax liabilities + period forms generated (cross-ref FORM) | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | Critical | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-014 | Files available after approval (not gated on payment) | Approved (not paid) run | Open Files |  | PAYE/SSNIT/bank file downloadable | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | Critical | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-015 | Gap: journal flag logged only | Approve with "post journal entries" on | Approve; check Finance + audit |  | Flag recorded in audit; NO entries posted to Finance — matches §25 | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | Medium | P3 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-LIFE-016 | Mark Paid side-effects | Approved Regular run w/ loans | Mark Paid |  | Loan decrement + calendar advance + payment status updates all fire | Mark Paid side-effects on Regular run #237: paid_at 2026-06-30, method Cash, approved_at present, finance_push_status deferred | Critical | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-017 | Mark Paid non-regular | Approved bonus run | Mark Paid |  | Loan decrement + status update; NO calendar advance | Mark Paid on non-Regular run verified: bonus run #88 → paid (paid_at 2026-06-26); off-cycle/bonus/termination reach PAID without advancing calendar | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-018 | Cancel with reason | Any pre-paid run | Cancel |  | Cancelled; reason in audit | draft run cancelled with reason (status 200); reason recorded in audit | Medium | P2 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-019 | Immutable audit per transition | Run through full lifecycle | Inspect pay-run audit log |  | Entry per transition: who/when/from/to/message; immutable | BLOCKED — UI-only — needs browser-driven (Playwright page) test | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-LIFE-020 | Edit blocked after processing | Processed run | Attempt edit employees |  | Blocked (no longer Draft) | edit blocked after processing (PUT → 422) | Medium | P2 | PASS | ✓ Verified | test-cases/Payroll
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## DEFECTS TRACKING
Payroll Lifecycle — Defects | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
DEFECT ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | ASSIGNED TO | STATUS | RESOLUTION DATE/TIME | LINKED TEST CASE ID
BUG-007 | [Medium/P3] Once a pay run reaches **Approved**, `cancel`, `reject`, and `return-to-previous` all return **422** — the only forward action is Mark-as-Paid, leaving no way to abort an erroneously-approved (unpaid) run |  | (dev) | Open — needs confirmation |  | TC-LIFE-008
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## NON-FUNCTIONAL TESTING
Payroll Lifecycle — Non-Functional | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
TEST CASE ID | PERFORMANCE CRITERIA | TEST SCENARIO | EXPECTED PERFORMANCE | ACTUAL PERFORMANCE | DEVIATION | COMMENTS
PT01 | Response time < 2 sec | Load Testing | Creating job roles should take < 2 sec | [Insert Observed Time] | [Insert Deviation] | [Insert Comments]
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: SECURITY TESTING
TEST CASE ID | SECURITY ASPECT TESTED | VULNERABILITY FOUND | RISK LEVEL
ST01 | Data Integrity | No issues | Low
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: USABILITY TESTING
TEST CASE ID | USERABILITY CRITERIA | USER TEST FEEDBACK
UT01 | Ease of use | Positive feedback from HR team
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: COMPATIBILITY TESTING
TEST CASE ID | PLATFORM TESTED | COMPATIBILITY ISSUES
CT01 | Windows, macOS | None
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )