## TEST CASES(FUNCTIONAL)
Deductions | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS |  | EXECUTIVE SUMMARY |  |  |  |  | COUNTS | PERCENTAGE (%)
|  | 2026-07-01 | Deffect count: Recommendations count: |  | Black | Pass/Fixed | Total Test Cases | 25 | Pass rate (of exec) | 100% |  | N# of Test Objectives | % of Fail
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed | PASS | 10 | Execution Date | 2026-07-01 |  | Pending Count | % of Pass
[5 empty] | Blue | Recommendations | FAIL | 0 | Environment | SBX |  | Pass Count | % of Pending
[7 empty] | BLOCKED | 15 |  |  |  | Fail Count | % of Recommendation
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com | [6 empty] | NOT APPLICABLE | 0 |  |  |  | Recommendation Count | No Status
TEST CASE ID | TEST CASE DESCRIPTION | PRE-CONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | TEST STATUS | COMMENTS/NOTES | ATTACHMENTS | Total | Total
TC-DED-001 | Create each deduction type | Admin | Create Statutory/Voluntary/Loan/Benefit/Custom |  | Saved with classification | BLOCKED — Pending implementation — admin-reachable; not yet ported into the registry | Low | P2 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-002 | Calc: Fixed | Fixed GH₵150 | Run |  | Deduction = 150.00 | fixed 150 ✓ (chargeable 3335, net 2710.62) | Critical | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-003 | Calc: % of Basic | 5% of 4,000 | Run |  | Deduction = 200.00 | % of basic 10% × 3000 = 300 ✓ (chargeable 3335, net 2560.62) | Critical | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-004 | Calc: % of Cash Emoluments | base set | Run |  |  | deduction percentage_of_cash_emoluments not accepted: {"calculation_method":["calculation_method 'percentage_of_cash_emolume — calc-method API contract not exposed for deductions | Critical | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-DED-005 | Calc: % of Net Pay (second pass) | %-of-net deduction | Run |  | Computed in pass 2 after tax + protected pay on realistic net | % of net (2nd pass): deduction 286.06 == 10% of net-before-deduction 2860.62 (method=percentage_of_net_pay) | Critical | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-006 | Before-Tax reduces PAYE base | Before-tax deduction | Run |  | PAYE base reduced; tax lower | before-tax reduces PAYE base; PAYE==oracle ✓ (chargeable 3035, net 2613.12) | Critical | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-007 | After-Tax net only | After-tax deduction | Run |  | Net reduced; PAYE base unchanged | after-tax reduces net only ✓ (chargeable 3335, net 2660.62) | Critical | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-008 | Default = After Tax | Deduction with treatment unspecified | Run |  | Treated as After Tax | default tax treatment = After Tax (stored: after_tax default) | High | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-009 | Priority recorded | Two deductions diff priority | Inspect |  | Priority stored for trim order | priority recorded for trim order (priority=5) | High | P2 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-010 | Eligibility scope | Deduction scoped to person | Run others |  | Applied only to scope | eligibility scope honored: deduction applied only to assigned employee (in-scope has D10 line; out-of-scope does not) | High | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-DED-011 | Override window | Override dates | Run inside/outside |  | Applied only inside window | deduction window gating not verifiable via off-cycle run (applies all assigned items by design); needs regular-run harness | High | P1 | BLOCKED | Blocked | test-cases/Deductions
TC-DED-012 | Permission gating | Non-permitted user | CRUD UI + API |  | Blocked both | BLOCKED — Bucket C: permission-gating ("non-permitted user") requires a non-admin session; blocked by BUG-011 (role accounts have no Payroll module entitlement). | High | P1 | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | test-cases/Deductions
TC-DED-013 | %-of-net not in pass 1 | %-of-net + before-tax mix | Inspect pipeline |  | %-of-net deferred to pass 2, not pass 1 | deduction percentage_of_net not accepted — %-of-net calc-method API contract not exposed | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-001 | Floor: absolute | Rule net ≥ GH₵1,000 | Run heavy-deduction employee |  | Floor = 1,000 enforced per mode | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-002 | Floor: % of gross | Rule 40% gross | Run |  | Floor = 40% × gross | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-003 | Floor: % of basic | Rule 50% basic | Run |  | Floor = 50% × basic | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-004 | Hard Block | Hard-block rule, deductions breach floor | Process run |  | Employee Error; run cannot process until deductions reduced | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Critical | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-005 | Partial Apply + Alert | Partial rule, breach | Process |  | Deductions trimmed by priority until floor met; carryover recorded; alert raised | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Critical | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-006 | Alert Only | Alert-only rule, breach | Process |  | Nothing trimmed; warning raised; net below floor allowed | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Medium | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-007 | Statutory never trimmed | Partial rule, large PAYE+Tier1 | Process |  | PAYE & Tier1 untouched; only catalog deductions trimmed | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Critical | P1 | PASS | ✓ Verified | test-cases/Deductions
TC-PROT-008 | Priority trim order | Multiple deductions varied priority | Partial trim |  | Lowest priority trimmed first; highest survives longest | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | High | P1 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-009 | Carryover recorded | Partial trim | Inspect run |  | Deferred amount recorded as carryover | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | High | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-010 | Gap: no auto-recovery | Carryover from prior run | Next run |  | Carryover NOT auto-recovered — matches §25 | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Medium | P3 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-011 | Audit storage | Any protected-pay employee | Inspect snapshot |  | Rule, floor, net before/after, deferred stored | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Medium | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
TC-PROT-012 | Floor exactly met (boundary) | Deductions bring net == floor | Process |  | No trim needed; net == floor; no carryover | BLOCKED — API contract not exposed: protected-pay-rules (see reports/07-requests-to-unblock.md) | Medium | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Deductions
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## DEFECTS TRACKING
Deductions — Defects | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
DEFECT ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | ASSIGNED TO | STATUS | RESOLUTION DATE/TIME | LINKED TEST CASE ID
DF01 | System crashes when creating job position roles | 1. Navigate to Recruitment module 2. Select 'Create Job Position' 3. Save | [Developer Name] | Open | [Insert Date] | TC01
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## NON-FUNCTIONAL TESTING
Deductions — Non-Functional | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
TEST CASE ID | PERFORMANCE CRITERIA | TEST SCENARIO | EXPECTED PERFORMANCE | ACTUAL PERFORMANCE | DEVIATION | COMMENTS
PT01 | Response time < 2 sec | Load Testing | Creating job roles should take < 2 sec | [Insert Observed Time] | [Insert Deviation] | [Insert Comments]
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: SECURITY TESTING
TEST CASE ID | SECURITY ASPECT TESTED | VULNERABILITY FOUND | RISK LEVEL
ST01 | Data Integrity | No issues | Low
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: USABILITY TESTING
TEST CASE ID | USERABILITY CRITERIA | USER TEST FEEDBACK
UT01 | Ease of use | Positive feedback from HR team
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: COMPATIBILITY TESTING
TEST CASE ID | PLATFORM TESTED | COMPATIBILITY ISSUES
CT01 | Windows, macOS | None
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )