## TEST CASES(FUNCTIONAL)
Payslips | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS |  | EXECUTIVE SUMMARY |  |  |  |  | COUNTS | PERCENTAGE (%)
|  | 2026-07-01 | Deffect count: Recommendations count: |  | Black | Pass/Fixed | Total Test Cases | 16 | Pass rate (of exec) | 100% |  | N# of Test Objectives | % of Fail
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed | PASS | 7 | Execution Date | 2026-07-01 |  | Pending Count | % of Pass
[5 empty] | Blue | Recommendations | FAIL | 0 | Environment | SBX |  | Pass Count | % of Pending
[7 empty] | BLOCKED | 9 |  |  |  | Fail Count | % of Recommendation
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com | [6 empty] | NOT APPLICABLE | 0 |  |  |  | Recommendation Count | No Status
TEST CASE ID | TEST CASE DESCRIPTION | PRE-CONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | TEST STATUS | COMMENTS/NOTES | ATTACHMENTS | Total | Total
TC-SLIP-001 | Download gated on Paid+Paid | Paid run, employee payment Paid | Open employee row |  | Download Payslip available | BLOCKED — UI-only — report export rendered client-side | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-002 | Not available before Paid | Approved (not paid) run | Open employee row |  | Download Payslip NOT shown | BLOCKED — API contract not exposed: catalog approval-activation trigger (see reports/07) | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-003 | Not available if employee not paid | Paid run, employee status not Paid | Open row |  | Download not shown for that employee | BLOCKED — Bucket C: payslip retrieval API not exposed (/employees/{id}/payslips → SPA-HTML, no JSON contract); cannot assert "unavailable if not paid" via API. | Medium | P2 | BLOCKED | Blocked – Missing API Contract | test-cases/Payroll
TC-SLIP-004 | Snapshot-based (no recompute) | Paid employee | Download; compare to stored snapshot |  | PDF values == snapshot exactly | BLOCKED — UI-only — report export rendered client-side | High | P1 | BLOCKED | Blocked – Browser Only | test-cases/Payroll
TC-SLIP-005 | PDF identity/header | Paid employee | Inspect PDF |  | Org header/logo, period, pay date, ref, name/code/dept/position/TIN present | BLOCKED — UI-only — report export rendered client-side | Medium | P2 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-006 | PDF payment details masked | Paid employee | Inspect PDF |  | Method, bank/branch or network, masked account/wallet | BLOCKED — UI-only — needs browser-driven (Playwright page) test | Medium | P2 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-007 | PDF earnings exclude BIK | Employee with BIK | Inspect Earnings section |  | Cash earnings + cash benefits only; BIK absent | BLOCKED — UI-only — report export rendered client-side | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-008 | Two deduction groups | Employee w/ statutory + other deductions | Inspect PDF |  | Statutory Deductions + Other Deductions shown separately | BLOCKED — UI-only — report export rendered client-side | Medium | P2 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-009 | Same-name combine (loans) | Employee w/ 2 employer loans | Inspect PDF |  | Single summed "Employer Loan Repayment" line; audit unaffected | BLOCKED — UI-only — report export rendered client-side | Medium | P2 | BLOCKED | Blocked – Browser Only | test-cases/Payroll
TC-SLIP-010 | PDF totals + words | Paid employee | Inspect PDF |  | Gross, total deductions, net pay, net-in-words all correct | BLOCKED — UI-only — report export rendered client-side | High | P1 | PASS | ✓ Verified | test-cases/Payroll
TC-SLIP-011 | List own payslips | Staff logged in | GET `/my/payslips` |  | Only own payslips listed | BLOCKED — Credentials: "list own payslips" is staff self-service (/my/payslips); requires a Staff session, not provisioned. | High | P1 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Payroll
TC-SLIP-012 | Current payslip | Staff | GET `/my/payslips/current` |  | Current period payslip returned | BLOCKED — Credentials: "current payslip" is staff self-service (/my/payslips); requires a Staff session, not provisioned. | High | P1 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Payroll
TC-SLIP-013 | Download one + all | Staff | Download single + bulk |  | PDFs returned, scoped to self | BLOCKED — Needs Manager/Staff credentials (cross-role / self-service not testable as Admin) | High | P1 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Payroll
TC-SLIP-014 | No admin perm needed | Staff (no admin perms) | Call self-service API |  | Allowed | BLOCKED — Needs Manager/Staff credentials (cross-role / self-service not testable as Admin) | High | P1 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Payroll
TC-SLIP-015 | Cross-employee blocked (IDOR) | Staff A | Request Staff B's payslip id |  | Denied (cross-ref SEC-014) | BLOCKED — Needs Manager/Staff credentials (cross-role / self-service not testable as Admin) | Critical | P1 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Payroll
TC-SLIP-016 | Gap: this-app My Payslips placeholder | This app router | Open Self-Service → My Payslips |  | Unused placeholder (real UI in kedebah_v2_pim) — matches §23/§25 | BLOCKED — Needs Manager/Staff credentials (cross-role / self-service not testable as Admin) | Low | P3 | BLOCKED | Blocked – Missing Credentials/Persona | test-cases/Payroll
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## DEFECTS TRACKING
Payslips — Defects | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
DEFECT ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | ASSIGNED TO | STATUS | RESOLUTION DATE/TIME | LINKED TEST CASE ID
DF01 | System crashes when creating job position roles | 1. Navigate to Recruitment module 2. Select 'Create Job Position' 3. Save | [Developer Name] | Open | [Insert Date] | TC01
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## NON-FUNCTIONAL TESTING
Payslips — Non-Functional | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
TEST CASE ID | PERFORMANCE CRITERIA | TEST SCENARIO | EXPECTED PERFORMANCE | ACTUAL PERFORMANCE | DEVIATION | COMMENTS
PT01 | Response time < 2 sec | Load Testing | Creating job roles should take < 2 sec | [Insert Observed Time] | [Insert Deviation] | [Insert Comments]
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: SECURITY TESTING
TEST CASE ID | SECURITY ASPECT TESTED | VULNERABILITY FOUND | RISK LEVEL
ST01 | Data Integrity | No issues | Low
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: USABILITY TESTING
TEST CASE ID | USERABILITY CRITERIA | USER TEST FEEDBACK
UT01 | Ease of use | Positive feedback from HR team
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: COMPATIBILITY TESTING
TEST CASE ID | PLATFORM TESTED | COMPATIBILITY ISSUES
CT01 | Windows, macOS | None
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )