## TEST CASES(FUNCTIONAL)
Enterprise Onboarding | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS |  | EXECUTIVE SUMMARY |  |  |  |  | COUNTS | PERCENTAGE (%)
|  | 2026-07-01 | Deffect count: Recommendations count: |  | Black | Pass/Fixed | Total Test Cases | 23 | Pass rate (of exec) | 100% |  | N# of Test Objectives | % of Fail
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed | PASS | 10 | Execution Date | 2026-07-01 |  | Pending Count | % of Pass
[5 empty] | Blue | Recommendations | FAIL | 0 | Environment | SBX |  | Pass Count | % of Pending
[7 empty] | BLOCKED | 13 |  |  |  | Fail Count | % of Recommendation
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com | [6 empty] | NOT APPLICABLE | 0 |  |  |  | Recommendation Count | No Status
TEST CASE ID | TEST CASE DESCRIPTION | PRE-CONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULTS | ACTUAL RESULTS | SEVERITY | PRIORITY | TEST STATUS | COMMENTS/NOTES | ATTACHMENTS | Total | Total
TC-ENT-001 | Enterprise central login |  |  |  | Authenticates | PASS — temp password accepted, advances past login. |  |  | PASS | ✓ Verified | evidence/browser/enterprise/A-after-login.png
TC-ENT-002 | Forced password change |  |  |  | Password changes; proceeds | PASS — Admin password changed (current=temp → new=QaPhase4_admin_9X!) and proceeded to module launcher. |  |  | PASS | ✓ Verified | evidence/browser/enterprise/B-change-password.png
TC-ENT-003 | Business selection |  |  |  | Business context set | PASS — lands on /R-2171-WRY/clients/select-module with William & Co selected (switch-business dropdown available). |  |  | PASS | ✓ Verified | evidence/browser/enterprise/D-module-launcher.png
TC-ENT-004 | Enterprise Module Launcher |  |  |  | Payroll module tile present and launchable | FAIL/BLOCKED — launcher renders 'No modules found' for the Payroll Admin account on William & Co; NO Payroll module tile → cannot launch Payroll. Module not provisioned for the new role accounts at the enterprise level. |  |  | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | evidence/browser/enterprise/D-module-launcher.png
TC-ENT-005 | Launch Payroll module → Payroll app |  |  |  | Reaches Payroll application | BLOCKED — no Payroll module tile to launch (see TC-ENT-004); never reaches payroll.kedebah.com for these accounts. |  |  | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | evidence/browser/enterprise/D-module-launcher.png
TC-ENT-FORGOT-manager | Forgot-password reset request (Manager) |  |  |  | Reset link sent | PASS — flow works; 'We have emailed your password reset link.' sent to dwetornam@gmail.com. Completion is EMAIL-GATED (requires the inbox link — not accessible to QA). |  |  | PASS | ✓ Verified | evidence/browser/enterprise-manager/F-forgot-2.png
TC-ENT-FORGOT-reports | Forgot-password reset request (Reports) |  |  |  | Reset link sent | PASS — 'We have emailed your password reset link.' sent to dwetornam+2@gmail.com. Completion is email-gated. |  |  | PASS | ✓ Verified | evidence/browser/enterprise-reports/F-forgot-2.png
TC-ENT-MOD-admin | Admin module access |  |  |  | Payroll module visible | CONFIRMED EMPTY — 'No modules found' for Admin too. |  |  | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | evidence/browser/enterprise-admin/D-module-launcher.png
TC-ENT-MOD-employee | Employee module access |  |  |  | Payroll module visible (if entitled) | CONFIRMED EMPTY — launcher shows 'No modules found'; Employee has NO modules → cannot enter Payroll. Confirms BR-020 is systemic (not Admin-specific). |  |  | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | evidence/browser/enterprise-employee/D-module-launcher.png
TC-ENT-MOD-manager | Manager module access |  |  |  | Payroll module visible if entitled | CONFIRMED EMPTY — 'No modules found' for Manager too. All 4 roles now confirm BUG-011 (systemic, no module access). |  |  | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | evidence/browser/enterprise-manager/D-module-launcher.png
TC-ENT-MOD-reports | Reports module access |  |  |  | Payroll module visible if entitled | CONFIRMED EMPTY — 'No modules found' for Reports too (logged in via reset). |  |  | BLOCKED | Blocked – Missing Module Entitlement (BUG-011) | evidence/browser/enterprise-reports/D-module-launcher.png
TC-ENT-PW-employee | Password reset (Employee) |  |  |  | Password changes; user proceeds | PASS — temp iM25NapSO5 accepted → forced change committed → password now QaPhase4_employee_9X!; reached module launcher. |  |  | PASS | ✓ Verified | evidence/browser/enterprise-employee/E-final.png
TC-ENT-PW-manager | Password reset + login (Manager) |  |  |  | Authenticates, password usable | PASS — reset password 'password#23e' accepted; it was itself flagged must-change → set new 'Payroll2026#e'; reached module launcher. |  |  | PASS | Affected by Open Defect (BUG-012) | evidence/browser/enterprise-manager/E-final.png
TC-ENT-PW-reports | Password reset (Reports) |  |  |  | One password accepted → change screen | BLOCKED — BOTH temp IrLyR66kvk AND QaPhase4_reports_9X! rejected ('Invalid password'). Unknown password state; needs owner reset/confirm. |  |  | BLOCKED | Blocked – Browser Only | evidence/browser/enterprise-reports/A-after-login.png
TC-RBAC-admin-login | Login as admin |  |  |  | Authenticated per-role session | credentials VALID (login accepted → forced 'Change Password' screen) but session NOT established — after the forced password change the app redirects to a SEPARATE identity domain 'https://sbxkedebah-v2.npontu.com/clients/sign-in' (multi-domain SSO). Automation cannot yet complete the cross-domain handshake. NOT missing-credentials; an SSO/forced-change automation gap. |  |  | BLOCKED | Blocked – Missing Credentials/Persona | evidence/browser/role-admin/1-dashboard.png
TC-RBAC-employee-login | Login as employee |  |  |  | Authenticated per-role session | credentials VALID (login accepted → forced 'Change Password' screen) but session NOT established — after the forced password change the app redirects to a SEPARATE identity domain 'https://sbxkedebah-v2.npontu.com/clients/sign-in' (multi-domain SSO). Automation cannot yet complete the cross-domain handshake. NOT missing-credentials; an SSO/forced-change automation gap. |  |  | BLOCKED | Blocked – Missing Credentials/Persona | evidence/browser/role-employee/1-dashboard.png
TC-RBAC-manager-login | Login as manager |  |  |  | Authenticated per-role session | credentials VALID (login accepted → forced 'Change Password' screen) but session NOT established — after the forced password change the app redirects to a SEPARATE identity domain 'https://sbxkedebah-v2.npontu.com/clients/sign-in' (multi-domain SSO). Automation cannot yet complete the cross-domain handshake. NOT missing-credentials; an SSO/forced-change automation gap. |  |  | BLOCKED | Blocked – Missing Credentials/Persona | evidence/browser/role-manager/1-dashboard.png
TC-RBAC-reports-login | Login as reports |  |  |  | Authenticated per-role session | credentials VALID (login accepted → forced 'Change Password' screen) but session NOT established — after the forced password change the app redirects to a SEPARATE identity domain 'https://sbxkedebah-v2.npontu.com/clients/sign-in' (multi-domain SSO). Automation cannot yet complete the cross-domain handshake. NOT missing-credentials; an SSO/forced-change automation gap. |  |  | BLOCKED | Blocked – Missing Credentials/Persona | evidence/browser/role-reports/1-dashboard.png
TC-URB-001 | Admin create user |  |  |  | User created | [api] PASS — subscription now ACTIVE (was gated): created Payroll Manager(#4)/Employee(#5)/Reports(#6)/Admin(#7) with real emails, status=active. (Supersedes earlier BLOCKED — subscription was renewed.) |  |  | PASS | ✓ Verified | scratchpad/iam.mjs
TC-URB-002 | Admin role CRUD (create/edit/delete) |  |  |  | Roles can be created, edited, deleted | [api] PASS — POST /roles → 201, PUT /roles/{id} → 200, DELETE /roles/{id} → 204 (verified on AIQA_ roles, all cleaned up). NOT subscription-gated. |  |  | PASS | ✓ Verified | scratchpad/users-lifecycle.mjs capture
TC-URB-003 | Assign permissions to a role |  |  |  | Permissions attach to the role (permissions_count increases) | [api] BLOCKED — silent no-op: PUT returns 200 but permissions_count stays 0 for all field variants; POST /roles/{id}/permissions → 405 (GET/HEAD only). Seeded roles have permissions but they cannot be assigned via the exposed API. |  |  | BLOCKED | Blocked – Missing API Contract | scratchpad/users3.mjs capture
TC-URB-004 | Assign role to user |  |  |  | Role attaches to user | [api] PASS — POST /roles/{id}/assign-users works; all 4 users now show their role (Manager/Employee/Reports/Admin), verified via GET /users. (Note: role_ids in the create payload is a SILENT NO-OP — assignment must use the dedicated endpoint.) |  |  | PASS | ✓ Verified | scratchpad/iam.mjs
TC-URB-005 | Login as created user (admin-set password) |  |  |  | User can log in with the admin-set password | [api+browser] BLOCKED — admin-set password is a SILENT NO-OP: POST /users accepts `password` but login returns 422 'Invalid password' (same for a deliberately-wrong password). Browser login as the new Manager stays on the login page. Users must self-activate via their email to set a password; per-role login/permission-enforcement testing cannot proceed. |  |  | BLOCKED | Blocked – Missing Credentials/Persona | evidence/browser/iam/2-after-login.png
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## DEFECTS TRACKING
Enterprise Onboarding — Defects | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
DEFECT ID | DEFECT DESCRIPTION | STEPS TO REPRODUCE | ASSIGNED TO | STATUS | RESOLUTION DATE/TIME | LINKED TEST CASE ID
BUG-011 | [Critical/P0] A user created in Payroll (with a role assigned) is **not granted the Payroll module** at the enterprise level — after login + password change + business selection, the Enterprise Module Launcher shows **"No modules found"**, so the user can never reach Payroll | 1. Create a user in Payroll (`POST /users`) and assign a role (`POST /roles/{id}/assign-users`). 2. Log in as that user at `https://sbxkedebah-v2.npontu.com/clients/sign-in`. 3. Complete the forced "Change Password" (`/clients/change-password-required`). 4. Land on the Enterprise Module Launcher (`/ | (dev) | Open |  | TC-ENT-004, TC-ENT-005, TC-ENT-MOD-admin, TC-ENT-MOD-employee
BUG-012 | [Major/P1] `POST /users` accepts a `password` (and `password_confirmation`) but **silently ignores it** — the new user cannot log in with it (`/login` → "Invalid password"), so an admin cannot provision a working credential at creation time | 1. `POST /users { user_data: { …, password: "X", password_confirmation: "X" } }` → 200, user created. 2. Log in as that user with password "X" → **"Invalid password"** (auth rejects it). 3. The accept-and-ignore is silent: no warning that the password was not set. | (dev) | Open |  | TC-URB-005, TC-ENT-PW-manager, TC-ENT-PW-reports
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )

## NON-FUNCTIONAL TESTING
Enterprise Onboarding — Non-Functional | TEST NUMBER | TEST EXECUTION DATE | TEST SUMMARY |  | KEY INDICATORS
|  |  | Deffect count: Recommendations count: |  | Black | Pass/Fixed
TEST DESCRIPTION | TEST DESIGNED BY | LAST UPDATED BY | LAST UPDATE DATE |  | Red | Failed
[5 empty] | Blue | Recommendations
TEST ENVIRONMENT: https://payroll.kedebah.com (SBX) + enterprise portal sbxkedebah-v2.npontu.com
TEST CASE ID | PERFORMANCE CRITERIA | TEST SCENARIO | EXPECTED PERFORMANCE | ACTUAL PERFORMANCE | DEVIATION | COMMENTS
BR-020 | Bug | Newly-created role users authenticate, change password, and select the business, but the Enterprise Module Launcher shows 'No modules found' — they cannot enter the Payroll module at all. | The Payroll module tile is present and launchable for a provisioned Payroll user. | Enterprise Modules section empty ('No modules found for ""'). | Critical/P0 | FAIL — Grant the Payroll module to the role accounts in the enterprise portal (or auto-provision the module when a payroll user
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: SECURITY TESTING
TEST CASE ID | SECURITY ASPECT TESTED | VULNERABILITY FOUND | RISK LEVEL
ST01 | Data Integrity | No issues | Low
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: USABILITY TESTING
TEST CASE ID | USERABILITY CRITERIA | USER TEST FEEDBACK
UT01 | Ease of use | Positive feedback from HR team
TEST ENVIRONMENT: [SBX] / [ BETA ] / [ PROD ] TEST TYPE: COMPATIBILITY TESTING
TEST CASE ID | PLATFORM TESTED | COMPATIBILITY ISSUES
CT01 | Windows, macOS | None
General Observation: |  | LOGIN:
1. Login error issues - Resolved |  | Phone Version Average Loading Time (Login)
2. Assign Users to Hub Issues - Resolved |  | Android 10 ( keeps loading- unable to login )
3. Apk version for Android version 10- Pending |  | Android 11 ( 2 mins )
4. "Automatic Login into a Hub" issue after installation on QA phone (Android v 14) - Pending |  | Android 13 ( 40 secs )
* (Couldn't replicate issue on another Android v. 14 ) |  | Android 14 ( 40s )